## Instructions
Add a tab for the new week
Copy the template from the previsous sheet

## Jan 22-28
Items | Update
Date on which you worked on the project. | January 23, January 26, January 28
Number of hours spent on that day. | 1/2 hour, 1/2 hour, 1/2 hour
Type of component, implementation or document. | Project Charter
Which specific part did you work with, e.g. requirement number or section of a document. (Mention multiple if necessary) | Section 2, Section 3.2, Section 3.5, Section 5
Brief summary (3-4 sentences) of what was accomplished during this time. | 1. Established roles within the team with fellow team members 2. Established in the Project Charter what the deliverables of the project were. 3. Wrote out the Risks, Constraints, and Assumptions for the project. 4. Signed the project charter document with teammates
Total number of hours worked during the week. | 1.5 hours

## Jan 29-Feb 4
Items | Update
Date on which you worked on the project. | January 30th, Feburary 2nd
Number of hours spent on that day. | 1/2 hour, 1/2 hour
Type of component, implementation or document. | SRS Document
Which specific part did you work with, e.g. requirement number or section of a document. (Mention multiple if necessary) | Section 1.2, Section 3
Brief summary (3-4 sentences) of what was accomplished during this time. | 1. Coordinated with team who was responsible for each part of the SRS document. 2. Worked on submitting the scope of the submission/quiz section of the project. 3. Helped contribute to making the user stories.
Total number of hours worked during the week. | 1 hour

## Feb 5-11
Items | Update
Date on which you worked on the project. | Feburary 6th, Feburary 9th, Febuary 11th
Number of hours spent on that day. | 1/2 hour, 1 hour, 1/2 hour
Type of component, implementation or document. | SRS Document
Which specific part did you work with, e.g. requirement number or section of a document. (Mention multiple if necessary) | Section 3.2, Section 3.3
Brief summary (3-4 sentences) of what was accomplished during this time. | 1. Made 3 of the Functional Requirements 2. Made 2 of the Use Cases 3. Coordinated with team in collaboration of the previous 2 tasks
Total number of hours worked during the week. | 2 hours

## Feb 12-18
Items | Update
Date on which you worked on the project. | February 13th, February 16th
Number of hours spent on that day. | 1/2 hour, 1/2 hour
Type of component, implementation or document. | SRS Document
Which specific part did you work with, e.g. requirement number or section of a document. (Mention multiple if necessary) | Section 3.4, Section 4.1
Brief summary (3-4 sentences) of what was accomplished during this time. | 1. Wrote up the Non-Functional Requirements related to Availability and Security 2. Discussed with team the desired Sequence Diagram formats 3. Made the Sequence Diagrams for Use Cases 2 and 3
Total number of hours worked during the week. | 1 hour

## Feb 19-25
Items | Update
Date on which you worked on the project. | Februrary 20th
Number of hours spent on that day. | 1/2 hour
Type of component, implementation or document. | SRS Document
Which specific part did you work with, e.g. requirement number or section of a document. (Mention multiple if necessary) | Section 1, Section 2, Section 3, Section 4
Brief summary (3-4 sentences) of what was accomplished during this time. | 1. Went through the document with the group to make sure everything is correct 2. Helped delete lines not needed for final submission 3. Finalized SRS Doc Version 1
Total number of hours worked during the week. | 1/2 hour

## Feb 26- Mar 4
Items | Update
Date on which you worked on the project. | February 27th, March 2nd, March 4th
Number of hours spent on that day. | 1/2 hour, 1/2 hour, 1/2 hour
Type of component, implementation or document. | Design Document
Which specific part did you work with, e.g. requirement number or section of a document. (Mention multiple if necessary) | Section 2.3, Section 3.1, Section 3.2
Brief summary (3-4 sentences) of what was accomplished during this time. | 1. Collaborated with team on tasks for Design Document 2. Filled out two lesson components (Test and Lesson) 3. Started working on the User Interface Model
Total number of hours worked during the week. | 1.5 hours

## Mar 5- Mar 18
Items | Update
Date on which you worked on the project. | March 6th, March 16th, March 18th
Number of hours spent on that day. | 1/2 hour, 1/2 hour, 1/2 hour
Type of component, implementation or document. | Design Document, Sprint Planning Document
Which specific part did you work with, e.g. requirement number or section of a document. (Mention multiple if necessary)
Brief summary (3-4 sentences) of what was accomplished during this time. | 1. Finished the Design Document with team 2. Discussed Roles for Sprint 1, and filled out Sprint 1 Document with Team 3. Began using PyCharm as the IDE for the project, and discussed documentation standard with team
Total number of hours worked during the week. | 1.5 hours

## Mar 19- Mar 25
Items | Update
Date on which you worked on the project. | March 20th, March 21st, March 23rd, March 24th, March 25th
Number of hours spent on that day. | 1 hour, 1 hour, 2 hours, 2 hours, 1 hour
Type of component, implementation or document. | Design Document, Sprint Planning Document, PyNotebook Lesson Interface
Which specific part did you work with, e.g. requirement number or section of a document. (Mention multiple if necessary)
Brief summary (3-4 sentences) of what was accomplished during this time. | 1. Discussed with Team our progress with Sprint 1 2. Completed most of the tasks required for Lesson Interfacing 3. Pushed completed work into the Project Repository
Total number of hours worked during the week. | 7 hours

## Mar 26 - Apr 1
Items | Update
Date on which you worked on the project. | March 27th, March 28th, March 30th, April 1st
Number of hours spent on that day. | 1 1/2 hour, 1 hour, 2 1/2 hours, 2 hours
Type of component, implementation or document. | Sprint Planning Document, Estimation Template, PyNotebook Lesson Interface
Which specific part did you work with, e.g. requirement number or section of a document. (Mention multiple if necessary)
Brief summary (3-4 sentences) of what was accomplished during this time. | 1. Created tasks for Sprint 2 with Team 2. Continued working on unfinished tasks from Sprint 1 3. Started Sprint 2 Tasks
Total number of hours worked during the week. | 7 hours

## Apr 2 - Apr 8
Items | Update
Date on which you worked on the project. | Apr 2nd, Apr 3rd, Apr 6th, Apr 7th, Apr 8th
Number of hours spent on that day. | 1 hour, 1 hour, 2 hours, 2 hours, 2 hours
Type of component, implementation or document. | PyNotebook Lesson Interface
Which specific part did you work with, e.g. requirement number or section of a document. (Mention multiple if necessary)
Brief summary (3-4 sentences) of what was accomplished during this time. | 1. Completed Unfinished Sprint 1 Tasks 2. Integrated Lesson Interface 3. Discussed with teammates next steps
Total number of hours worked during the week. | 8 hours