## Instructions
Add a tab for the new week
Copy the template from the previsous sheet

## Jan 26-Feb 2
Items | Update
Date on which you worked on the project. | 1/26/2026 & 2/1/2026
Number of hours spent on that day. | 30 minutes each day
Type of component, implementation or document. | Project Charter and SRS Document Editing
Which specific part did you work with, e.g. requirement number or section of a document. (Mention multiple if necessary) | Project Charter Revisons within the requirements section. SRS Document completing Section 1.4 Overview
Brief summary (3-4 sentences) of what was accomplished during this time. | Just basic finalization of the project charter in order to submit. Focused on revising and editing the team's work. For the SRS, completed my section 1.4 (Overview). Used the Overview template in brightspace to complete that section.
Total number of hours worked during the week. | 1

## Feb 2-Feb 9
Items | Update
Date on which you worked on the project. | 2/3/2026, 2/8,2026
Number of hours spent on that day. | 1,1 respectfully
Type of component, implementation or document. | SRS Document
Which specific part did you work with, e.g. requirement number or section of a document. (Mention multiple if necessary) | Requirements (3.2.1, 3.2.2, 3.2.4, and 3.2.8). User stories (REQ1-4).
Brief summary (3-4 sentences) of what was accomplished during this time. | 1. Firstly, created the first four user stories that defined lessons, interfacing, and the IDE 2. Then used those user stories to define my requirements within the document. 3. Additionally, sectioned off future sections for the group in order to better plan out the document. 4.
Total number of hours worked during the week. | 2

## Feb 9 - Feb 16
Items | Update
Date on which you worked on the project. | 2/10/2026, 2/13/2026
Number of hours spent on that day. | 1,1 respectfully
Type of component, implementation or document. | SRS Document
Which specific part did you work with, e.g. requirement number or section of a document. (Mention multiple if necessary) | Use Cases 4,5 and 6. Sequence Diagrams 4.1.4, 4.1.5, and 4.1.6. Section 3.4.1 and 3.4.2
Brief summary (3-4 sentences) of what was accomplished during this time. | 1. Firstly, I finished up my use cases based on the requirements that I wrote in the previous week. 2. Using those use cases, I worked on the sequence diagrams that follow those cases. 3. And finished up my section within 3.4 that we divided amongst group members in class. 4.
Total number of hours worked during the week. | 2

## Feb 23 - Mar 2
Items | Update
Date on which you worked on the project. | 2026-02-24
Number of hours spent on that day. | 1
Type of component, implementation or document. | SDS
Which specific part did you work with, e.g. requirement number or section of a document. (Mention multiple if necessary) | Domain Models)
Brief summary (3-4 sentences) of what was accomplished during this time. | 1. Completed the 2 components for the SDS, scanner and QuestionStorage 2. Followed the template and Vince's completed component as a general guidelines toward completing. 3. Finished up my parts by cleaning up and also checking for continuity among the rest of the groups work and mine. 4. (ACCIDENTALLY DELETED THESE SENTENCES)
Total number of hours worked during the week. | 1

## Mar 2 - Mar 9
Items | Update
Date on which you worked on the project. | 3/4, 3/6
Number of hours spent on that day. | 1, 1
Type of component, implementation or document. | SDS
Which specific part did you work with, e.g. requirement number or section of a document. (Mention multiple if necessary) | Components 3.3 and 3.4, General Clean-up
Brief summary (3-4 sentences) of what was accomplished during this time. | 1. Completed the 2 components for the SDS, scanner and QuestionStorage 2. Followed the template and Vince's completed component as a general guidelines toward completing. 3. Finished up my parts by cleaning up and also checking for continuity among the rest of the groups work and mine. 4.
Total number of hours worked during the week. | 2

## Mar 23 - Mar 30
Items | Update
Date on which you worked on the project. | 3/24, 3/25
Number of hours spent on that day. | 3, 2
Type of component, implementation or document. | Sprinnt 1 Implementation
Which specific part did you work with, e.g. requirement number or section of a document. (Mention multiple if necessary) | Tasks relating toward the demo for the Review Meeting (Scanner Function, General Test Interfacing, etc.)
Brief summary (3-4 sentences) of what was accomplished during this time. | 1. Continuing the work from last week, I was able clean up the scanner functionality. 2. Was able to fix a bug regarding the other members to run the file, specifically with the flaskwebgui implementation. 3. Organized html files to match with Andrew's standard in order to clean up code. 4. Ensured the demo for the Review Meeting was clean with scanning and question pulling.
Total number of hours worked during the week. | 5

## Mar 30 - Apr 7
Items | Update
Date on which you worked on the project. | 3/31, 4/1
Number of hours spent on that day. | 2, 2
Type of component, implementation or document. | Sprint 2 Week #1
Which specific part did you work with, e.g. requirement number or section of a document. (Mention multiple if necessary) | Beginning Sprint 2 implementation, UI upgrade, integration between team member's parts
Brief summary (3-4 sentences) of what was accomplished during this time. | 1. Moving forward by improving the UI of the demo in order to promote a more finished product. 2. Upgraded the logic of the html in order to keep integration of Vince and Andrew's peices to be smoother 3. Bug fixed various problems so that everyone in the group could run the demo 4. Walked through the integration process with the rest of the team.
Total number of hours worked during the week. | 4

## Apr 7 - Apr 13
Items | Update
Date on which you worked on the project. | 4/8, 4/9
Number of hours spent on that day. | 3, 2
Type of component, implementation or document. | Sprint 2 Week #2 + Review Meeting
Which specific part did you work with, e.g. requirement number or section of a document. (Mention multiple if necessary) | Completetion of Sprint #2 implementation, Full product integration, Demo setup for Review Meeting
Brief summary (3-4 sentences) of what was accomplished during this time. | 1. Was able to fix our big problem concerning the connection between Andrew's IDE and my scanner. 2. Tested some edge cases for our code input in order to ensure a smooth presentation on Friday 3. Fixed the formatting issues with my quiz generation to get a better overall look 4. Succeeded in the full integration of all the team's parts for the demo
Total number of hours worked during the week. | 5

## Apr 13 - Apr 20
Items | Update
Date on which you worked on the project. | 4/17, 4/19
Number of hours spent on that day. | 1, 4
Type of component, implementation or document. | Sprint 3 Work
Which specific part did you work with, e.g. requirement number or section of a document. (Mention multiple if necessary) | Started my work on Sprint 3
Brief summary (3-4 sentences) of what was accomplished during this time. | 1. Started the week with general planning from the group in order to finish out our project! 2. Most of the work was toward the end of the week, working on my final implementation for quiz integration 3. The quiz integration proved to take up more time than expected, due to the pulling of correct answers within our code
Total number of hours worked during the week. | 5

## Apr 20 - Apr 27
Items | Update
Date on which you worked on the project. | 4/21, 4/23
Number of hours spent on that day. | 2, 2
Type of component, implementation or document. | Finishing Sprint #3 and final implementation
Which specific part did you work with, e.g. requirement number or section of a document. (Mention multiple if necessary) | Answer generation, lesson window updating, and general bug fixing. Final Review Meeting preperation.
Brief summary (3-4 sentences) of what was accomplished during this time. | 1. Finished up my quiz generation peice from last week, updated the formatting on the html to make it a better look 2. Completed the reset quiz logic, in order to pull random questions that fit the requests from Dr. Gupta. 3. Bug fixed with Andrew on the lesson window logic, and then tested to be ready for Friday!
Total number of hours worked during the week. | 4